## Schedule
Student academic portifolio system	319	Date
1. Initiating	18	11/27/2024
1.1. Develop Project Charter	10	11/27/2024
1.1.1. Identify goals and objectives	2	11/27/2024					Task	Start date	Days
1.1.2. Develop strategies and plans	4	11/28/2024					1. Initiating	11/27/2024	9
1.1.3. Research previous experience	2	3/28/2024					2. Planning	12/10/2024	147
1.1.4. Develop project charter	2	11/28/2024					3. Executing	07/03/2025	162
1.1.5. Project charter	0	11/29/2024					4. Monitoring and Controlling	2/19/2026	69
1.2. Identify Stakeholders	8	11/29/2024					5. Closing	5/27/2026	13
1.2.1. conduct planning workshop	1	11/29/2024
1.2.2. document project costs and benefites	1	12/01/2024
1.2.3. develop high level work breakdown structure	2	12/02/2024
1.2.4. conduct peer review	1	12/04/2024
1.2.5. prepare preliminary project scope statement	2	12/05/2024
1.2.6. Abstract scope statement	1	12/09/2024
2. Planning	60	12/10/2024
2.1. Develop Scope Management Plan	13	12/10/2024
2.1.1. Document Scope management plan	3	12/10/2024
2.1.2. specify deliverables and acceptance criteria	3	12/15/2024
2.1.3. Define scope	3	12/18/2024
2.1.4. document assumptions	3	12/23/2024
2.1.5. Scope statement	1	12/26/2024
2.2. Develop Schedule Management Plan	11	12/29/2024
2.2.1. build wbs	3	12/29/2024
2.2.2. develop recourse plan	3	01/02/2025
2.2.3. prepare project estimates	2	01/07/2025
2.2.4. define dependencies and develop project schedule	1	01/07/2025
2.2.5. document assumptions	1	01/08/2025
2.2.6. project schedule	1	01/09/2025
2.3. Develop Cost Management Plan	5	01/14/2025
2.3.1. prepare financial plan	3	01/16/2025
2.3.2. document assumptions	1	01/18/2025
2.3.3. financial plan	1	01/20/2025
2.4. Develop Quality Management Plan	2	01/21/2025
2.4.1. Document quality management plan	1	02/21/2025
2.4.2. Quality management plan	1	02/30/2025
2.5. Develop Resource Management Plan	3	03/05/2025
2.5.1. Develop orgnaization structure	1	03/18/2025
2.5.2. Develop staffing plan	2	03/28/2025
2.6. Develop Communications Management Plan	2	04/07/2025
2.6.1. Conduct meetings	1	04/25/2025
2.6.2. Communication Criteria	1	05/08/2025
2.7. Develop Risk Management Plan	7	5/22/2025
2.7.1. identify risks	3	5/30/2025
2.7.2. analyze risks	2	06/04/2025
2.7.3. develop a strategy to mitigate the risks	1	06/06/2025
2.7.4. document risks	1	06/07/2025
2.8. Develop Procurement Management Plan	7	06/10/2025
2.8.1. determine procurment requirment	2	06/10/2025
2.8.2. define sub contractor scope	1	06/12/2025
2.8.3. identify potential sub contractors	1	6/13/2025
2.8.4. identify contract type	1	6/14/2025
2.8.5. document plan	1	6/17/2025
2.8.6. procurment plan	1	6/18/2025
2.9. Develop Stakeholder Engagement Plan	4	6/19/2025
2.9.1. determine engagement methods	1	6/19/2025
2.9.2. establish feedback plan	1	6/20/2025
2.9.3. create an engagement timeline	1	6/21/2025
2.9.4. evaluate communicaction	1	6/24/2025
2.10. Develop project management plan	6	6/25/2025
2.10.1. document project management plan	5	6/25/2025
2.10.2. project management plan	1	07/02/2025
3. Executing	165	07/03/2025
3.1. Direct And Manage Project Work	28	07/03/2025
3.1.1. manage process data	20	07/03/2025
3.1.2. provide general office support	8	7/31/2025
3.2. Manage Quality	42	08/12/2025
3.2.1. participate in walkthroughs	12	08/12/2025
3.2.2. conduct inspections	10	8/28/2025
3.2.3. conduct project reviews	10	09/11/2025
3.2.4. facilitate continuos improvement	10	9/25/2025
3.3. Manage Resources	55	10/09/2025
3.3.1. obtain recources	30	10/09/2025
3.3.2. conduct team orientation	10	11/20/2025
3.3.3. assign responsiblties	10	12/04/2025
3.3.4. project team	5	12/18/2025
3.4. Manage Communications	7	12/25/2025
3.4.1. review progress	6	12/25/2025
3.4.2. document progress	1	01/02/2026
3.5. Conduct Procurements	33	01/03/2026
3.5.1. bidder confrence	5	01/03/2026
3.5.2. proposal evaluation methods	10	01/10/2026
3.5.3. choose potential conttractors	10	1/24/2026
3.5.4. procurment negatioation	5	02/07/2026
3.5.5. select procurments	3	2/14/2026
4. Monitoring and Controlling	69	2/19/2026
4.1. Monitor And Control Project Work	9	2/19/2026
4.1.1. Authorize work	7	2/19/2026
4.1.2. Manage project records	2	2/28/2026
4.2. Perform Integrated Change Control	10	03/04/2026
4.2.1. Manage scope	3	03/04/2026
4.2.2. Manage reuirements	3	03/07/2026
4.2.3. Control decisions	3	03/12/2026
4.2.4. Control changes	1	3/17/2026
4.3. Validate and control Scope	5	3/18/2026
4.3.1. Manage project Acceptance test	3	3/18/2026
4.3.2. Manage scope changes	2	3/21/2026
4.4. Control Schedule	8	3/25/2026
4.4.1. Maintain project schedule	5	3/25/2026
4.4.2. Maintain work plans	3	04/01/2026
4.5. Control Costs	3	04/04/2026
4.5.1. Monitor cost/schedule variance	1	04/04/2026
4.5.2. Control costs	1	04/07/2026
4.5.3. Maintatin financial plan	1	04/08/2026
4.6. Control Quality	4	04/09/2026
4.6.1. Perform quality control	2	04/09/2026
4.6.2. Participate in testing	1	04/11/2025
4.6.3. Measure quality levels	1	4/14/2026
4.7. Control Resources	6	4/15/2026
4.7.1. Monitor resource utilization	3	4/15/2026
4.7.2. Compare actual vs. planned resource utilization	1	4/18/2026
4.7.3. Take corrective actions	1	4/21/2026
4.7.4. Adjust resource plans	1	4/22/2026
4.8. Monitor Communications	7	4/23/2026
4.8.1. Manage communications	3	4/23/2026
4.8.2. Meet with team	1	4/28/2026
4.8.3. Monitor team morale	1	4/29/2026
4.8.4. Conduct team performance review	2	4/30/2026
4.9. Monitor Risks	9	05/02/2026
4.9.1. Manage risks	9	05/02/2026
4.10. Control Procurements	6	5/15/2026
4.10.1. Managing procurement relationships	3	5/15/2026
4.10.2. Monitoring Contract performance	2	5/20/2026
4.10.3. Making changes	1	5/22/2026
4.11. Monitor Stakeholder Engagement	2	5/23/2026
4.11.1. Monitor satisfaction	1	5/23/2026
4.11.2. Resolve issues	1	5/26/2026
5. Closing	7	5/27/2026
5.1. Close Project	7	5/27/2026
5.1.1. Acceptance test	2	06/05/2026
5.1.2. summraize project results	1	06/09/2026
5.1.3. review performance	1	06/10/2026
5.1.4. close the project records	1	06/11/2026
5.1.5. review financial performance	2	06/12/2026

## 3Point-estimate
Task	Days	cost per day $	subtotal(optimistic)	subtotal(most likely)	subtotal(pessimistic)
Examination System	319
1. Initiating	18
Develop Project Charter	10	500	4500	5000	5250
Identify Stakeholders	8	2860	20592	22880	24024
2. Planning	60
Develop Project Management Plan	6	2780	15012	16680	17514
Develop Scope Management Plan	13	4000	46800	52000	54600
Develop Schedule Management Plan	11	4120	40788	45320	47586
Develop Cost Management Plan	5	2500	11250	12500	13125
Develop Quality Management Plan	2	1670	3006	3340	3507
Develop Resource Management Plan	3	1250	3375	3750	3937.5
Develop Communications Management Plan	2	2500	4500	5000	5250
Develop Risk Management Plan	7	1880	11844	13160	13818
Develop Procurement Management Plan	7	3350	21105	23450	24622.5
Develop Stakeholder Engagement Plan	4	1500	5400	6000	6300
3. Executing	165
Direct And Manage Project Work	28	1565	39438	43820	46011
Manage Quality	42	2140	80892	89880	94374
Manage Resources	55	2380	117810	130900	137445
Manage Communications	7	2500	15750	17500	18375
Conduct Procurements	33	3850	114345	127050	133402.5
4. Monitoring and Controlling	69
Monitor And Control Project Work	9	3080	24948	27720	29106
Perform Integrated Change Control	10	775	6975	7750	8137.5
Validate Scope and control	5	1000	4500	5000	5250
Control Schedule	8	1250	9000	10000	10500
Control Costs	3	3350	9045	10050	10552.5
Control Quality	4	1100	3960	4400	4620
Control Resources	6	500	2700	3000	3150
Monitor Communications	7	840	5292	5880	6174
Monitor Risks	9	2350	19035	21150	22207.5
Control Procurements	6	1000	5400	6000	6300
Monitor Stakeholder Engagement	2	1000	1800	2000	2100
5. Closing	7
Close Project	7	2500	15750	17500	18375
6- Reserves (20% of Total estimates)			157500	175000	183750
Total Project Costs			822312	913680	1256304

## Budget
Category	Budget in $
	Months
	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15
Human Resources	3567	4924.533333	4924.533333	4924.533333	4924.533333	4924.533333	4924.533333	4924.533333	4924.533333	4924.533333	4924.533333	4924.533333	4924.533333	4924.533333	4924.533333
Purchases Team	200	4000	36934	36934	0	0	0	0	0	0	0	0	0	0	0
Equipment	0	0	0	0	20880	18467	0	0	0	0	0	0	0	0	0
Tools	0	0	0	0	20880	18467	0	0	0	0	0	0	0	0	0
Development Team	0	0	0	0	36934	36934	36934	0	0	0	0	0	0	0	0
Training	0	0	3357.636364	3357.636364	3357.636364	3357.636364	3357.636364	3357.636364	3357.636364	3357.636364	3357.636364	3357.636364	3357.636364	0	0
Commercial Office	3389.88	2462.266667	2462.266667	2462.266667	2462.266667	2462.266667	2462.266667	2462.266667	2462.266667	2462.266667	2462.266667	2462.266667	2462.266667	2462.266667	2462.266667
Controlling Team	0	0	0	0	0	0	0	0	0	0	0	12311.33333	12311.33333	12311.33333	0
Maintenance Team	0	0	0	0	0	0	0	11080.25	11080.25	11080.25	11080.25	11080.25	11080.25	11080.25	11080.25
Marketing Team	0	0	0	0	0	0	0	0	0	0	0	0	29547.33333	29547.33333	29547.33333
Testing software Team	0	0	0	0	0	0	0	7386.875	7386.875	7386.875	7386.875	7386.875	7386.875	7386.875	7386.875
Research Team	2890.2	2890.2	2890.2	2890.2	2890.2	2890.2	2890.2	2890.2	2890.2	2890.2	2890.2	2890.2	2890.2	2890.2	2890.2
Reserves	10356.9	10356.9	10356.9	10356.9	10356.9	10356.9	10356.9	10356.9	10356.9	10356.9	10356.9	10356.9	10356.9	10356.9	10356.9
Total	20403.98	24633.9	60925.53636	60925.53636	102685.5364	97859.53636	60925.53636	42458.66136	42458.66136	42458.66136	42458.66136	54769.99469	84317.32802	80959.69166	68648.35833
Total cumulated	20403.98	45037.88	105963.4164	166888.9527	269574.4891	367434.0255	428359.5618	470818.2232	513276.8845	555735.5459	598194.2073	652964.202	737281.53	818241.2217	886889.58